|  |  |
| --- | --- |
| **TIME FRAME** | **TASK** |
| November 17 – December 10, 2021 | Timeline to choose a topic and submit it |
| December 13, 2021 | Initial meeting with supervisor and start working on Dissertation |
| January 10 – 14, 2022 | Final set of exams |
| December 13, 2021 – February 3, 2022 | Start working on software section of the dissertation |
| February 4, 2022 | First progress meeting with supervisor |
| February 4 – 25, 2022 | Continue working on software based on feedback from the first progress meeting |
| February 25, 2022 | Second progress meeting with supervisor |
| February 25 – March 18, 2022 | Continue working on software based on feedback from the second progress meeting |
| March 18 2022 | Third progress meeting with supervisor |
| March 18 – 27, 2022 | Start and complete Preliminary Project Report and send to supervisor for feedback |
| March 28 – April 1, 2022 | Finalise and submit Preliminary Project Report |
| April 1 – May 13, 2022 | Start final stages of software development |
| May 13, 2022 | Fourth progress meeting with supervisor |
| May 13 – June 24, 2022 | Final stages of software development |
| June 24, 2022 | Fifth progress meeting with supervisor |
| June 24 – July 1, 2022 | Create an outline for final report |
| July 1 – 15, 2022 | Carry out software tests, collect results and make final conclusions |
| July 15, 2022 | Sixth and final progress meeting with supervisor |
| July 15 – 29, 2022 | Start and complete final report and proofread |
| July 30 – August 6, 2022 | Window to make sure everything is in order |
| August 6, 2022 | Submit Dissertation Report and Software |
| August 7, 2022 (5pm) | Create video presentation and edit to fit submission requirements |
| August 8, 2022 (5pm) | Final deadline to submit Report and Software |
| August 10, 2022 (5pm) | Final deadline to submit Video Presentation |

Tabla

Descripción generada automáticamente

*Project Calendar (According to the module page)*